## Sheet1
ID | Type | Description | Likelihood | Impact | Mitigation or action | Owner | Status | Link
R1 | Risk | duration or campaign leaks into model features, inflating performance | Medium | High | Explicit drop list in src/preprocessing.py; unit test in tests/ asserting forbidden columns are absent | Analytics lead | Open | Module 1 leakage risk; Sprint 2
R2 | Risk | Only 11.27% of records are subscribers, so accuracy misleads | High | Medium | Report recall at top 30%, PR-AUC and lift; stratified splits; test class weights | Analytics lead | Open | Module 1 success goals; Sprint 3
R3 | Risk | Efficiency gains concentrate on retired and student customers (age extremes) and widen the age-band recall gap beyond 10 points | Medium | High | Age-by-job crosstab in notebook 04; recall by age band with confidence intervals; document the efficiency-fairness trade-off | Analytics lead; ethics committee | Open | Module 1 fairness target; RCA finding
R4 | Risk | Very small categories (for example rare education levels) give unstable fairness estimates | High | Medium | Minimum group-size rule; bootstrap confidence intervals; merge sparse categories and document it | Analytics lead | Open | Module 1 fairness evaluation; Sprint 3
R5 | Risk | Month and economic columns encode the 2008-2010 period, and random cross-validation overstates performance | Medium | High | Time-ordered train/test split; economic columns excluded from the baseline model; sensitivity check | Analytics lead | Open | Module 1 poor-transfer risk; Sprint 3
R6 | Risk | Segments change with random seed or feature scaling | Medium | Medium | Fix random seeds; compare segments across runs; report profiles and sizes | Analytics lead | Open | Module 1 segmentation requirement; Sprint 3
R7 | Risk | Raw or processed data committed to the public repo | Low | High | .gitignore rules in place; review git status before every commit; keep outputs aggregate-only | Data protection owner | Mitigating | Module 1 privacy risk; every sprint
R8 | Risk | Duplicate rows put the same record in both train and test sets | Medium | Medium | Check df.duplicated() in notebook 01; deduplicate and document the count | Analytics lead | Open | Sprint 2
I1 | Issue | Stray files named like version numbers (for example =1.20.0) appeared in the working tree during setup, likely from an unquoted version specifier in a pip command | n/a | Low | Deleted before commit; quote version specifiers; review git status before every commit | Analytics lead | Closed | Sprint 1
I2 | Issue | An Excel-converted copy of the dataset was in data/raw instead of the original CSV | n/a | Medium | Replaced with the original CSV; record the checksum in the data dictionary | Analytics lead | Closed | Sprint 1; Module 1 provenance
D1 | Dependency | shap 0.51.0 on pandas 3.0.6 and scikit-learn 1.9.1: only import-tested, not explanation-tested | n/a | High | Smoke test on a small model in Sprint 2; pin versions or downgrade pandas if it fails | Analytics lead | Open | requirements.txt; Sprint 2
D2 | Dependency | Fairlearn 0.15.0 metric API compatibility with the pinned scikit-learn | n/a | High | Smoke test equalized-odds metrics on a dummy model in Sprint 2 | Analytics lead | Open | requirements.txt; Sprint 2
D3 | Dependency | Streamlit Community Cloud needs the app and requirements in a public repo, but data cannot be committed | n/a | High | Dashboard reads precomputed aggregate outputs only; no row-level data in the repo | Analytics lead | Open | Module 1 deployment plan; Sprint 4
D4 | Dependency | Module 4 modelling depends on the Module 3 processed data; the Module 5 dashboard depends on Module 4 outputs | n/a | Medium | Keep tickets small; agree output file formats at each sprint review | Analytics lead | Open | Sprint plan
D5 | Dependency | UCI dataset availability and CC BY 4.0 attribution | n/a | Low | Keep checksum and an unchanged local copy; cite Moro et al. (2012) wherever the data is used | Analytics lead | Open | Module 1 provenance
A1 | Assumption | contact, month and day_of_week describe the current call and are not eligible as model inputs under the Module 1 rule | n/a | Medium | Confirm in the data dictionary; revisit if the rule is changed | Analytics lead | To confirm | Data dictionary
A2 | Assumption | Economic columns are confounders and are excluded from the baseline model | n/a | Medium | Test the effect in a sensitivity run after the baseline | Analytics lead | To confirm | Data dictionary; Sprint 3
A3 | Assumption | Outreach allocation logic lives in src/evaluation.py because the Module 1 tree has no separate file | n/a | Low | Revisit if the file grows too large | Analytics lead | To confirm | Repo structure
A4 | Assumption | campaign is the final contact total including the subscribing contact, so per-call returns cannot be measured | n/a | Medium | Document the limit; use only for retrospective evaluation | Analytics lead | Confirmed from UCI documentation (verify) | RCA
A5 | Assumption | Contact counts are a proxy for RM effort because the data has no call time or cost | n/a | Medium | State the proxy in every KPI report | Business owner | Open | Module 1 constraint